## WBS
WBS ID | Task Name | Description | Owner | Phase
1.0 | Project Initiation | Define project goals and feasibility | Project Owner | Initiation
1.1 | Project Charter | Prepare and approve project charter | Project Owner | Initiation
2.0 | Requirement Analysis | Gather and analyze requirements | Project Owner | Planning
2.1 | Business Requirements | Document business requirements (BRD) | Project Owner | Planning
2.2 | Product Requirements | Document product requirements (PRD) | Project Owner | Planning
3.0 | System Design | Design system workflow and architecture | Project Owner | Design
3.1 | Workflow Design | Define document flow and AI process | Project Owner | Design
3.2 | UI Design | Design Streamlit dashboard layout | Project Owner | Design
4.0 | Development | Develop application components | Project Owner | Execution
4.1 | Document Upload Module | Implement file upload functionality | Project Owner | Execution
4.2 | AI Analysis Module | Integrate AI-based document analysis | Project Owner | Execution
4.3 | Reporting Module | Generate daily and weekly reports | Project Owner | Execution
4.4 | Analytics Dashboard | Create charts and visual analytics | Project Owner | Execution
5.0 | Testing & Validation | Test system functionality and outputs | Project Owner | Testing
5.1 | Functional Testing | Verify features against requirements | Project Owner | Testing
5.2 | UAT | Validate system with business perspective | Project Owner | Testing
6.0 | Documentation | Prepare project documentation | Project Owner | Documentation
6.1 | User Documentation | Prepare user guide and notes | Project Owner | Documentation
6.2 | Project Closure Report | Document outcomes and lessons learned | Project Owner | Documentation
7.0 | Project Closure | Close project and finalize deliverables | Project Owner | Closure