## Risk Register
Risk ID | Risk Description | Category | Probability (Low/Medium/High) | Impact (Low/Medium/High) | Risk Level | Mitigation Strategy | Owner | Status
R1 | AI-generated analysis may produce inaccurate summaries | Technical | Medium | High | High | Use fallback logic, confidence scoring, and manual review recommendation | Project Owner | Open
R2 | Poor quality or unreadable input documents | Operational | Medium | Medium | Medium | Validate file formats and handle extraction errors gracefully | Project Owner | Open
R3 | OpenAI API unavailability or quota limits | Technical | Low | High | Medium | Implement fallback analysis and error handling | Project Owner | Open
R4 | Scope creep due to addition of advanced AI features | Project Management | Low | Medium | Low | Strict scope definition and change control | Project Owner | Open
R5 | Performance issues with large document uploads | Technical | Medium | Medium | Medium | Limit file size and optimize text extraction | Project Owner | Open
R6 | Data security concerns for uploaded documents | Security | Low | High | Medium | Avoid persistent storage and use session-based processing | Project Owner | Open
R7 | Time constraints due to solo project execution | Schedule | Medium | Medium | Medium | Phase-wise planning and realistic timelines | Project Owner | Open
R8 | User misinterpretation of AI-generated insights | Business | Low | Medium | Low | Provide clear summaries, confidence indicators, and disclaimers | Project Owner | Open